## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | Sarah | Done | 1 | 1
Drivers' Documentation | Sarah | Done | 1 | 1
Low Level Design
Functions' Flowchart | Sarah | Done | 1 | 1
Summary
Document File | Sarah | Done | 2 | 3
Implementation & Unit Testing
MCAL Module
GPT Driver | Ahmed | Done | 16 | 16
SERV Module
PWM Manager | Ahmed | Done | 8 | 8
APP Module
App Driver | Ahmed | Done | 2 | 2
Testing
Documentation
Test Protocol Excel Sheet | Ahmed | Done | 1 | 1
System Testing
Test APP | Ahmed | Done | 1 | 1
Final Requirements Review | Ahmed | Done | 1 | 0.5
Video
Video Recording | All Team | Done | 1 | 1

## Test Protocol
Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
Unit Testing
SYSTICK Driver
TC_GPIO_001 | Test initialization and callback function | 1- define 1000ms as delay time and pass it to systick driver through systick_init 2- toggle an output pin in a task which is set as a callback function 3- debug | The output pin will toggle every 1 second | As excepected | Pass
GPIO Driver
TC_GPIO_001 | Test gpio_pin_init | 1- define an instance as an output 2- check the registers' value of gpio port used while debugging | registers used will be modified after initialzation | As excepected | Pass
TC_GPIO_002 | Test gpio_pin_write high then low | 1- define an instance as an output 2- breakpoint before writing high 3- breakpoint before writing low 4- debug | gpiodata for the used port will be set then cleared | As excepected | Pass
TC_GPIO_003 | Test gpio_pin_read | 1- define an instance as an output 2- define an instance as an input 3- write high on the output pin when high is writen on the input pin 4- debug | when input pin is high, the output pin will be high when input pin is low, the output pin will be low | As excepected | Pass
TC_GPIO_004 | Test gpio_pin_toggle | 1- define an instance as an output 2- breakpoint before toggling in while loop 3- debug | gpiodata for the used port will keep changing | As excepected | Pass
APP Module
App Testing
TC_APP_001 | Test application | press the sw 5 times | 1.The RGB LED is OFF initially 2. The PWM signal has a 500ms duration 3. Pressing SW1: 3.1. After the first press, the Green LED will be on with a 30% duty cycle. 3.2. After the second press, the Green LED will be on with a 60% duty cycle. 3.3. After the third press, the Green LED will be on with a 90% duty cycle. 3.4. After the fourth press, the Green LED will be off 3.5. After the fifth press, repeat from the beggining | As excepected | Pass