## Team Backlog
Team Backlog
Task Name | Assignee | Task Status | Expected Time to Finish (Hrs) | Actual Time to Finish (Hrs)
Design
High Level Design
Modules' Description | All Team | Done | 3 | 3
Drivers' Documentation | All Team | Done | 3 | 2
Low Level Design
Functions' Flowchart | All Team | Done | 3 | 5
Summary
Document File | All Team | Done | 2 | 3
Implementation
MCAL Module
GPIO Driver | Ahmed | Done | 8 | 8
HAL Module
Button Driver | Sarah | Done | 3 | 3
LED Driver | Sarah | Done | 3 | 3
APP Module
App Driver | Ahmed | Done | 2 | 2
Testing
Documentation
Test Protocol Excel Sheet | Ahmed | Done | 1 | 1
Unit Testing
Test MCAL | Ahmed | Done | 3 | 3
Test HAL | Ahmed | Done | 2 | 2
System Testing
Test APP | Ahmed | Done | 4 | 8
Final Requirements Review | Ahmed | Done | 1 | 0.5
Video
Video Recording | All Team | Done | 1 | 3

## Test Protocol
Test Protocol
Test Case ID | Test Case Description | Test Case Steps | Expected Result | Actual Result | Pass/Fail
Unit Testing
GPIO Driver
TC_GPIO_001 | Test gpio_pin_init | 1- define an instance as an output 2- check the registers' value of gpio port used while debugging | registers used will be modified after initialzation | As excepected | Pass
TC_GPIO_002 | Test gpio_pin_write high then low | 1- define an instance as an output 2- breakpoint before writing high 3- breakpoint before writing low 4- debug | gpiodata for the used port will be set then cleared | As excepected | Pass
TC_GPIO_003 | Test gpio_pin_read | 1- define an instance as an output 2- define an instance as an input 3- write high on the output pin when high is writen on the input pin 4- debug | when input pin is high, the output pin will be high when input pin is low, the output pin will be low | As excepected | Pass
TC_GPIO_004 | Test gpio_pin_toggle | 1- define an instance as an output 2- breakpoint before toggling in while loop 3- debug | gpiodata for the used port will keep changing | As excepected | Pass
APP Module
App Testing
TC_APP_001 | Test application | press the sw 6 times | 1.The RGB LED is OFF initially 2. Pressing SW1: 2.1. After the first press, the Red led is on 2.2. After the second press, the Green led is on 2.3. After the third press, the Blue LED is on 2.4. After the fourth press, all LEDs are on 2.5. After the fifth press, all LEDs are off 2.6 After the six press, repeat from the beggining | As excepected | Pass